## Sheet1
Ochilview Housing Association
Estate Inspections 2020-21
Summary by Area
Month | Planned | Actual | Target | % Completed
2020-04-01 | 10 | 0 | 10 | 0%
2020-05-01 | 11 | 0 | 11 | 0%
2020-06-01 | 10 | 0 | 10 | 0%
2020-07-01 | 18 | 18 | 18 | 100%
2020-08-01 | 10 | 10 | 10 | 100%
2020-09-01 | 11 | 11 | 11 | 100%
2020-10-01 | 10 | 10 | 10 | 100%
2020-11-01 | 18 |  | 18 | 0%
2020-12-01 | 10 |  | 10 | 0%
2021-01-01 | 11 |  | 11 | 0%
2021-02-01 | 10 |  | 10 | 0%
2021-03-01 | 18 |  | 18 | 0%
| 147 | 49 | 147 | 33.33%
Issues by Area
Area | Surveyed | Issues found |  | Action taken
Carlyle Street, High Valleyfield | 2020-10-28 | Various dumped items/debris throughout development. |  | Passed to Housing to contact tenants to arrange for removal.
|  | Area to front of no.11 requires planting out. |  | To be considered under landscaping budget.
Dunimarle Street, High Valleyfield | 2020-10-28 | Various dumped items/debris throughout development. |  | Passed to Housing to contact tenants to arrange for removal.
|  | Broken paving slab adjacent to no's 43/45. |  | Works order issued for repair.
Kinloss Court/Valleyfield Avenue, High Valleyfield | 2020-10-28 | Various dumped items/debris throughout development. |  | Passed to Housing to contact tenants to arrange for removal.
|  | Gutter leaking at pathway to side of no. 23. |  | Works order issued for repair.
Ochilview Drive, High Valleyfield | 2020-10-28 | Broken latch on gate of 54 & 56 |  | Works order issued for repair.
|  | Tree at no.44 growing too close to the buildings. |  | Obtaining quote to remove tree and roots.
Preston Crescent, High Valleyfield | 2020-10-28 | Various dumped items/debris throughout development. |  | Passed to Housing to contact tenants to arrange for removal.
|  | Gutters requiring repair at no. 34. |  | Works order issued for repair.
Old Mill Lane, Oakley | 2020-10-28 | Various dumped items/debris throughout development. |  | Passed to Housing to contact tenants to arrange for removal.
|  | Fence posts in some shrub beds requiring repair. |  | Works order issued for repair.
|  | Light out in common stair of block 1-7. |  | Works order issued for repair.
|  | Service button not working and door not locking on block 17-23. |  | Works order issued for repair.
|  | Leaking overflow at block 17-23. |  | Works order issued for repair.
|  | Ivy needing removed and hedging trimmed at block 25-31. |  | Passed to landscape contractor to attend to.
Wardlaw Way/Connelly Court, Oakley | 2020-10-28 | Gate to side of no.5 requires repair. |  | Works order issued for repair.
|  | Gutter joint broken adjacent to no. 37. |  | Works order issued for repair.
South Avenue, Blairhall | 2020-10-28 | Hedges looking untidy. |  | Will obtain quote for removal and re-planting.
|  | Gutter leaking to rear of no.42 |  | Works order issued for repair.
Millbank Crescent, Clackmannan | 2020-10-28 | Gutters requiring repair throughout. |  | Works order issued for repair.
Tinian Crescent, Newmills | 2020-10-28 | Some dumped items through development. |  | Passed to Housing to contact tenants to arrange for removal.
|  | Gutters requiring clearing adjacent to 25-31. |  | Works order issued for repair.